## Tasks
Task | Duration
Review | 5
Launch | 1
Survey | 4
Prep | 2
Design | 6
Permit | 3

## Dependencies
Successor | Predecessor
Design | Permit
Prep | Survey
Design | Survey
Review | Design
Launch | Prep
Launch | Review

## Excluded archive
Unrelated historical total | 765432